## Test Plan
Online Banking Application
Prepared by Lusine Sargsyan
2024-08-18
Content
1. Introduction
2. Objectives
3. Scope
4. Environments
5. Hardware and Software
6. Entry and Exit criteria
7. Test strategy
8. Roles and responsibilities
9. Test schedule

## Introduction
The customer wants an online banking application supporting both desktop and mobile browsers. The application allows users to manage their bank accounts, transfer funds, pay bills, and view their transaction history. This Test Plan document describes the appropriate strategies, processes, workflows, and methodologies used to plan, organize, execute and manage testing of the software project.

## Objectives
1. The main purpose of the test plan is to ensure that the system meets the requirements (functional and non-functional): it means to validate the functionality, security, performance and compatibility of the online banking application.
All changes (including additions and deletions) to the requirements document, functional specification,design specification and so on will be documented and tested at the highest level of quality allowed within the remaining time of the project and within the ability of the test team.
2. The second objective is to find out and expose all issues and risks, assign them to appropriate (responsible) team members , communicate with project team, ensure taht all issues are reviewed and/or fixed before release. To fulfill it, detailed testing is required, using different test methods and properly reporting all the defects.

## Scope
1. In Scope:
Cross browser compatibility testing- that means to check how the application works on different platforms, the UI and the functionality on both desktop and mobile browsers on different operating systems.
Security testing - that means to check if the login and authentication process is secure and whether it is protected from unauthorized access or not. It's a high priority check.
Features testing - all the features described in requirements (transfer funds between accounts, pay bills, and view transaction history) should work properly and without unexpected failures.
Performance testing - it is needed to validate that the application works without failures and loading issues under high traffic during peak hours.
Compliance testing- checking if the data is protected via security checks to validate it meets industry-standard security practices.
2. Out of scope:
Third-part integration from backend side.
Accessibility testing
Writing and running automation scripts ( this is not covered by this test plan).

## Environments
Following environments are needed:
1. Development (coding and debugging issues)
2. Testing (testing purposes, including security and performance testing)
3. Pre-production (pre-production testings and the environment should be maximal identical to production)
4. Production (the live environment )

## Hardware and Software
1. Following hardware is needed:
Laptops
Mobile devices, including iPhones and Android phones from different generations and different brands for Android phones (most common used devices in the regions which the application is supporting)
Tablets, including iPads and Android tabs from different generations and different brands for Android tabs (most common used devices in the regions which the application is supporting)
2. Following browsers are needed:
Google Chrome
Safari
Edge
3. Following operating systems are needed:
Windows
Linux
macOS
Android (different versions of android from oldest to be supported to latest)
iOS (different versions of iOS from oldest to be supported to latest)
4. Tools
Jmeter (for performance testing)
(for security testing security specialist should fill the tool)

## Entry and Exit criteria
Entry Criteria
All the necessary environments are set up and working properly
All the necessary documentation are ready and available
All the necessary data is available
All the tools needed for testing are installed and working properly
All the requirements are discussed, reviewed and acceptable
Exit Criteria
The required level of test coverage is provided
No blocker or critical severity or high priority bugs are left without fixing
The deadlines are met
Further testing is out of budget
No high risk features/areas are left without testing (login/authorization, core banking features)

## Test strategy
Testing types
1. Functional testing - to validate that all the required features functioning properly.
2. Non-functional testing including:
Performance testing
Load testing
Usability testing
Security testing
5. Regression testing
6. Smoke and/or sanity testing.
7. Cross-browser and cross-platform testing.
8. Acceptance testing
Test design techniques to be used
1. Equivalent Partitioning
2.Boundary Value Analysis
3. State Transition
4. Pairwise Testing
5. Error Guessing
Test scenarios
1. Login and Authorization
2. Funds transfer
3. Bills/Payments
4. Transacion history
5. High traffic handling
6. Security checks
Bug reporting
1. Tools for reporting - JIRA, Testrail
2. Bug severety levels - Blocker, Critical, Major, Medium, Low
3. Reporting schedule - daily: as soon as founding a bug
4. Assignees - responsible team members/developers or pm/tech lead as it is discussed

## Roles and responsibilities
Test manager - responsible for communication coordination between team members and test progress reporting
QA Lead -responsible for test environments, test case creating and execution, test progress monitoring
QA Engineer - responsible for design, development and execution of test cases, test planning partisipation, bug reporting
Performance tester - responsible for performance/load testing
Security tester - a security specialist,either outsourced or within the company, responsible for security testing
Developers - responsible for debugging in providing information to QA Engineers
Business Analyst - responsible for proper requirements
Product Owner or other stakeholders - responsible for providing feedback on test coverage, schedule and priorities and approving readinnes to release

## Test schedule
Test schedule
1. Functional testing - 4 weeks
2. Cross-browser and cross-platform testing - 1 week
3. Performance/load tests - 1 week
4. Security testing - 1 week
5. Usability testing - 1week
6. Regression testing - 1 week
7. Smoke and/or sanity testing -3 days
8. Acceptance testing - 3 days