## Test Plan
Appcharge
Prepared by Lusine Sargsyan
2024-08-22
Content
1. Introduction
2. Objectives
3. Scope
4. Environments
5. Hardware and Software
6. Entry and Exit criteria
7. Test strategy
8. Roles and responsibilities
9. Test schedule

## Introduction
The stakeholders wants ensure that the platform allows users to add virtual goods to their store through a dashboard and sell the virtual goods to customers through the store. Appcharge is providing mobile gaming studios with a white-label web store solution to sell their virtual game goods outside of the game directly to their players with reduced fees. This Test Plan document describes the appropriate strategies, processes, workflows, and methodologies used to plan, organize, execute and manage testing of the software project.

## Objectives
1. The main purpose of the test plan is to ensure that the system meets the requirements (functional and non-functional): it means to validate the functionality, security and performance of the application.
All changes (including additions and deletions) to the requirements document, functional specification,design specification and so on will be documented and tested at the highest level of quality allowed within the remaining time of the project and within the ability of the test team.
2. The second objective is to find out and expose all issues and risks, assign them to appropriate (responsible) team members , communicate with project team, ensure that all issues are reviewed and/or fixed before release. To fulfill it, detailed testing is required, using different test methods and properly reporting all the defects.

## Scope
1. In Scope:
Security testing - that means to check if the login and authentication process is secure and whether it is protected from unauthorized access or not. It's a high priority check.
Features testing - all the features described in requirements (adding virtual goods to their store through a dashboard and sell the virtual goods to customers through the store) should work properly and without unexpected failures.
Performance testing - it is needed to validate that the application works without failures and loading issues under high traffic.
Security compliance testing- checking if the data is protected via security checks to validate it meets industry-standard security practices and can handle .
2. Out of scope:
Third-part integration from backend side.
Accessibility testing

## Environments
Following environments are needed:
1. Development (coding and debugging issues)
2. Testing (testing purposes, including security and performance testing)
3. Pre-production (pre-production testings and the environment should be maximal identical to production)
4. Production (the live environment )

## Hardware and Software
1. Following hardware is needed:
Laptops
Mobile devices, including iPhones and Android phones from different generations and different brands for Android phones (most common used devices in the regions which the application is supporting)
Tablets, including iPads and Android tabs from different generations and different brands for Android tabs (most common used devices in the regions which the application is supporting)
2. Following browsers are needed:
Google Chrome
Safari
Edge
3. Following operating systems are needed:
Windows
Linux
macOS
Android (different versions of android from oldest to be supported to latest)
iOS (different versions of iOS from oldest to be supported to latest)
4. Tools
Jmeter (for performance testing)
Web Dev tools
Security testing tools should be added by security specialist

## Entry and Exit criteria
Entry Criteria
All the necessary environments are set up and working properly
All the necessary documentation are ready and available
All the necessary data is available
All the tools needed for testing are installed and working properly
All the requirements are discussed, reviewed and acceptable
Exit Criteria
The required level of test coverage is provided
No blocker or critical severity or high priority bugs are left without fixing
The deadlines are met
Further testing is out of budget
No high risk features/areas are left without testing (login/authorization security, payment security, creating/selling products, performance)

## Test strategy
Testing types
1. Functional testing - to validate that all the required features functioning properly.
2. Non-functional testing including:
Performance testing
Load testing
Stress testing
Security testing
5. Regression testing
6. Smoke or sanity testing.
8. Acceptance testing
Test design techniques to be used
1. Equivalent Partitioning
2.Boundary Value Analysis
3. State Transition
4. Pairwise Testing
5. Error Guessing
Test scenarios/Check list(samples)
1. Login and Authorization
1.1. Check users can successfully login dashboard with valid data via username and password
1.2. Check users can't successfully login dashboard with invalid data via username and password
1.3. Check the "Forget password" button functioning properly
1.4. Check the "Reveal password ('eye' icon)" button functioning properly
1.5. Check if users can successfully log in to the dashbord via "Google login" with valid data
1.6. Check if users can't log in to the dashbord via "Google login" with invalid data
2. Creating virtual products via dashboard
2.1. Check that the user has access to the "Products" subsection from the "Studio" section.
2.2. Check the "Add New Product" button's functionality
2.3. Check that the fileds in "New Product" page can be filled as required.
2.4. Try to save product with only the required fileds filled in.
2.5. Try to save product with each required field not filled in.
2.6. Save the product with all fields filled in.
2.7. Check the "Upload" functionality.
2.8. Check Edit/Duplicate/Delete functionalities.
2.9. Check the "Update Product" functionality.
2.10. Check that the user has access to the "Bundles" subsection in the "Offers" section.
2.11. Check the "Add New Bundle" button's functionality.
2.12. Check that the fields in "Add New Bundle" can be filled as required.
2.13. Try to save the bundle with only the required fields filled in.
2.14. Try to save the bundle with each required field not filled in.
2.15. Save the bundle with all fields filled in.
2.16. Check the "Add Product" button on the "New Bundle" page.
2.17. Check the design preview section while filling in the fields.
2.18. Check Edit/Duplicate/Delete functionalities.
2.19. Check that the product is displayed in the store.
3. Selling Virtual Goods to customers via Store
3.1. Check if the customer can log in to the store.
3.2. Check if the customer can choose a product.
3.3. Check if the customer can be successfully navigated to the payment page.
3.4. Check if the customer can pay for the good via credit card.
3.5. Check if the customer can pay for the good via PayPal.
3.6. Check if the customer can pay for the good via Link.
3.7. Check if the customer can pay for the good via Google Pay.
3.8. Check that the customer can't buy the good with invalid data.
3.9. Check that the customer can't process the payment via card if not all required fields are filled in.
3.10. Check that all the details are properly displayed in the checkout details.
3.11. Check that the purchased item is displayed in Orders.
4. High traffic handling
4.1. Check that the app behaves as required under high traffic simulation on the web store.
4.2. Check the breaking point of the system.
4.3. Check if the response remains stable during load testing.
4.4. Check that the store performes as usual when load increases gradually.
4.5. Check that the store remains stable after a sudden load increase.
5. Security checks
5.1. Check access control management
5.2. Penetration testing
5.3. Check server access controls
5.4. Check entry points
5.5. Check session expiration
5.6. Test for brute force attack
5.7. Test for URL manipulation
Bug reporting
1. Tools for reporting - JIRA, Testrail
2. Bug severety levels - Blocker, Critical, Major, Medium, Low
3. Reporting schedule - daily: as soon as founding a bug
4. Assignees - responsible team members/developers or pm/tech lead as it is discussed
Automate test cases

## Roles and responsibilities
Test manager - responsible for communication coordination between team members and test progress reporting
QA Lead -responsible for test environments, test case creating and execution, test progress monitoring
QA Engineer - responsible for design, development and execution of test cases, test planning partisipation, bug reporting
Performance tester - responsible for performance/load testing
Security tester - a security specialist,either outsourced or within the company, responsible for security testing
Developers - responsible for debugging and providing information to QA Engineers
Business Analyst - responsible for proper requirements
Product Owner or other stakeholders - responsible for providing feedback on test coverage, schedule and priorities and approving readinnes to release

## Test schedule
Test schedule
1. Functional testing - 2 weeks
2. Performance/load tests - 1 week
3. Security testing - 1 week
4. Test cases automation - 1 week
5. Regression testing - 1 week
6. Smoke and/or sanity testing -3 days
7. Acceptance testing - 3 days